## Overview
PROCHECK Safety - User Use Cases & Backend Scope
Client: | Alejandra Ibarra Nunez (Ale)
Client email: | ale@procheeck.com
Project: | PROCHECK Safety - Mexican occupational safety training and certification platform
Prepared by: | Munas
Date: | 2026-07-19
Contact: | Munas
Purpose
Lock backend scope by mapping every user, use case, and gap. Any change from here on must be quoted separately.
Summary
Roles: | 8 (Principal Admin, Vendedor, Capacitador, Client, Client Admin, Subcontractor, Employee, Public Verifier)
Use cases: | 68
Endpoints: | 77
Entities: | 19
Modules: | 16
Top 5 CRITICAL gaps
1 | Vendedor role not implemented (schema + endpoints + guards + UI)
2 | Capacitador (instructor) role not implemented (schema + endpoints + guards + UI)
3 | No CFDI/SAT invoicing endpoint - blocks Mexican tax compliance
4 | No payment provider webhook - payments stuck in pending
5 | No refresh token / session revocation - security risk for a regulated LMS
Status legend
DONE | Implemented and verified in code
PARTIAL | Partial implementation, gaps remain
TODO | Not started, planned in scope
BLOCKED | Waiting on client decision or external dependency
CLARIFY | Requirement still ambiguous

## Roles
Role | Codename | Category | Description | Login | Isolation Rule | Backend Status
Principal Admin | PRINCIPAL_ADMIN | Internal | PROCHECK super admin. Full platform access across all tenants. | Yes | No isolation - can see all companies, users, courses, certificates | DONE
Vendedor (NEW) | VENDEDOR | Internal | Sales rep. Creates leads, closes deals, tracks commissions. | Yes | Sees only own leads and commissions; can view assigned client companies | TODO - NEW role added via client annotations. Not yet in schema or code.
Capacitador (NEW) | CAPACITADOR | Internal | Instructor. Delivers courses, records attendance, signs off completions. | Yes | Sees only assigned cohorts, courses, and enrolled students | TODO - NEW role added via client annotations. Not yet in schema or code.
Client | CLIENT | External | Company-level owner. Buys seats, oversees the whole client account. | Yes | Sees only own company data (users, enrollments, certs, invoices) | DONE
Client Admin | CLIENT_ADMIN | External | Delegated administrator inside a client company. Manages employees and subcontractors. | Yes | Sees only own company + linked subcontractor companies | DONE
Subcontractor | SUBCONTRACTOR | External | Third-party company linked to a client. Their employees can be enrolled by the client. | Yes | Sees only own company data; parent client can enroll them | DONE
Employee | EMPLOYEE | External | End learner. Takes courses, quizzes, receives certificates. | Yes | Sees only own enrollments, quiz results, and certificates | DONE
Public Verifier | PUBLIC | Public | Anyone verifying a DC-3 certificate via folio/QR. No account required. | No | Read-only public verification endpoint, no PII exposure | PARTIAL - endpoint exists, QR verification flow not documented

## Use Cases
ID | Role | Use Case | Trigger | Steps | Priority | Backend Status | Endpoint(s) | Gap Notes
62 | Capacitador | Login as instructor | Course delivery | Would use POST auth/login | HIGH | DONE | POST /api/auth/login
63 | Capacitador | Author or edit a course | Content assignment | Would PATCH courses; PUT modules | HIGH | DONE | PATCH /api/courses/{id}; PUT /api/courses/{id}/modules
66 | Capacitador | View learners assigned to my courses | Progress check | Would GET learners scoped | HIGH | DONE
68 | Capacitador | Issue completion certificate after live class | Session completed | Would POST cert issue | HIGH | DONE | POST /api/certificates/admin/issue
64 | Capacitador | Deliver a live session or cohort | Scheduled class | Would POST sessions | MEDIUM | DONE
65 | Capacitador | Grade quiz attempts for open-ended questions | Manual grading | Would PATCH attempt score | MEDIUM | DONE
67 | Capacitador | Upload teaching material to library | New content | Would POST uploads; POST library | MEDIUM | DONE | POST /api/uploads; POST /api/library
12 | Client | Register own company profile | Post-signup | POST company; PATCH profile | HIGH | DONE | POST /api/companies; PATCH /api/companies/{id}
13 | Client | Register a subcontractor company under my client | New subcontractor engagement | POST company with type=subcontractor and parentCompanyId | HIGH | DONE | POST /api/companies
14 | Client | View list of my subcontractors | Compliance review | GET companies/{id}/subcontractors | HIGH | DONE | GET /api/companies/{id}/subcontractors
15 | Client | Purchase courses (checkout) | Employee training plan | POST checkout with items | HIGH | PARTIAL | POST /api/payments/checkout | Provider webhook not exposed
16 | Client | Download tax invoice PDF | Accounting cycle | GET invoices; GET invoice PDF | HIGH | PARTIAL | GET /api/payments/me/invoices; GET /api/payments/invoices/{id}/pdf | CFDI stamping endpoint not visible
17 | Client | View compliance dashboard for my company | Weekly review | GET overview; GET learners | HIGH | PARTIAL | GET /api/analytics/overview; GET /api/analytics/learners | Per-company scoping not documented
18 | Client | Verify a subcontractor employee certificate | Site access check | GET certificate lookup by code | HIGH | DONE | GET /api/certificates/lookup/{code}
20 | Client | Assign a course to my employees in bulk | Compliance deadline | POST enrollments/assign with userIds | HIGH | DONE | POST /api/enrollments/assign
19 | Client | Raise a support ticket | Issue encountered | POST support ticket | MEDIUM | DONE | POST /api/support/tickets
21 | Client Admin | Invite employees to platform | New hires | POST users/invite | HIGH | DONE | POST /api/users/invite | No CSV bulk import
22 | Client Admin | Bulk assign NOM course to team | Annual training cycle | POST enrollments/assign | HIGH | DONE | POST /api/enrollments/assign
23 | Client Admin | Track team progress | Monthly report | GET enrollments; GET analytics learners | HIGH | PARTIAL | GET /api/enrollments; GET /api/analytics/learners | Scoping filter unclear
24 | Client Admin | Email a certificate to an employee | Employee request | POST cert email | MEDIUM | DONE | POST /api/certificates/{id}/email
25 | Client Admin | Deactivate an offboarded employee | HR offboarding | DELETE user | MEDIUM | DONE | DELETE /api/users/{id}
26 | Client Admin | Export learner CSV for internal reporting | Board meeting | GET analytics learners CSV | MEDIUM | DONE | GET /api/analytics/learners.csv
28 | Client Admin | Reset an employee password | Lockout | POST forgot-password on employee behalf | MEDIUM | PARTIAL | POST /api/auth/forgot-password | No admin-triggered reset endpoint
27 | Client Admin | Cancel an incorrect enrollment | User error | DELETE enrollment | LOW | DONE | DELETE /api/enrollments/{id}
29 | Client Admin | View unread notifications count | Login | GET notifications unread-count | LOW | DONE | GET /api/notifications/unread-count
36 | Employee | Login with company credentials | Assigned training | POST auth/login | HIGH | DONE | POST /api/auth/login
37 | Employee | Update own profile with CURP | First login | PATCH users/me with curp | HIGH | DONE | PATCH /api/users/me | CURP validation format not confirmed
39 | Employee | Recover forgotten password | Cannot login | POST forgot-password; POST reset-password | HIGH | DONE | POST /api/auth/forgot-password; POST /api/auth/reset-password
40 | Employee | Browse public course catalog | Self-enrollment interest | GET courses; GET course by slug | HIGH | DONE | GET /api/courses; GET /api/courses/slug/{slug}
41 | Employee | Self-enroll in an assigned NOM course | Assigned by admin | POST enrollments | HIGH | DONE | POST /api/enrollments
42 | Employee | Watch course videos and report progress | Study session | GET module watch; PATCH watch seconds; POST module complete | HIGH | DONE | GET /api/enrollments/{id}/modules/{moduleId}/watch; PATCH /api/enrollments/{id}/modules/{moduleId}/watch; POST /api/enrollments/{id}/modules/{moduleId}/complete
43 | Employee | Take end-of-course quiz | All modules complete | GET quiz; POST attempt | HIGH | DONE | GET /api/quizzes/by-course/{courseId}; POST /api/quizzes/{id}/attempts
44 | Employee | Download own DC-3 certificate PDF | Post-passing | GET certificates/me; GET cert PDF | HIGH | DONE | GET /api/certificates/me; GET /api/certificates/{id}/pdf | DC-3 template compliance not verified
45 | Employee | Request recertification when about to expire | Expiry notification | POST enrollment recertify | HIGH | PARTIAL | POST /api/enrollments/{id}/recertify | NOM-specific expiry windows not modeled
46 | Employee | View my enrolled courses and progress | Dashboard load | GET enrollments/me | HIGH | DONE | GET /api/enrollments/me
38 | Employee | Change password | Security best practice | POST auth/change-password | MEDIUM | DONE | POST /api/auth/change-password
47 | Employee | Read in-app notifications | Bell icon | GET notifications; POST read | MEDIUM | DONE | GET /api/notifications; POST /api/notifications/{id}/read
48 | Employee | Search safety library for reference docs | On-the-job question | GET library with q | MEDIUM | DONE | GET /api/library
49 | Employee | Open a support ticket | Access issue | POST support | LOW | DONE | POST /api/support/tickets
50 | Employee | Cancel a wrong enrollment | Wrong course | DELETE enrollment | LOW | DONE | DELETE /api/enrollments/{id}
51 | Employee | View past module completions | Progress review | GET completions | LOW | DONE | GET /api/enrollments/{id}/completions
1 | Principal Admin | Onboard a new client company | Sales contract signed | Login; Create company (type=client); Invite client_admin user; Send welcome email | HIGH | DONE | POST /api/companies; POST /api/users/invite
2 | Principal Admin | Create and publish a NOM course | New NOM regulation or content ready | POST course; PUT modules; PUT quiz; PATCH isPublished=true | HIGH | DONE | POST /api/courses; PUT /api/courses/{id}/modules; PUT /api/quizzes; PATCH /api/courses/{id}
5 | Principal Admin | View platform-wide KPIs | Weekly review | GET overview; GET courses; GET learners | HIGH | DONE | GET /api/analytics/overview; GET /api/analytics/courses; GET /api/analytics/learners
6 | Principal Admin | Export compliance report PDF | STPS audit request | Login; GET analytics report PDF | HIGH | DONE | GET /api/analytics/report.pdf | Date-range filter not documented
3 | Principal Admin | Issue a certificate manually | Offline course completion recorded | Login; Admin issue with userId courseId dc3Folio | MEDIUM | DONE | POST /api/certificates/admin/issue
4 | Principal Admin | Revoke a certificate | Fraud or invalidation | Find cert; POST revoke with reason | MEDIUM | DONE | POST /api/certificates/{id}/revoke
7 | Principal Admin | Investigate suspicious action via audit log | Security incident | GET audit with actor filter | MEDIUM | DONE | GET /api/audit | No CSV export
8 | Principal Admin | Respond to support tickets | Client ticket raised | GET tickets; PATCH with response and status | MEDIUM | DONE | GET /api/support/tickets; PATCH /api/support/tickets/{id} | No threaded replies
9 | Principal Admin | Deactivate an offboarded user | HR request | DELETE user | MEDIUM | DONE | DELETE /api/users/{id}
11 | Principal Admin | Manage document library items | New STPS document | POST library; PATCH library | MEDIUM | DONE | POST /api/library; PATCH /api/library/{id}
10 | Principal Admin | Upload company logo or DC-3 template asset | Branding update | POST uploads | LOW | DONE | POST /api/uploads
52 | Public Verifier | Verify a candidate certificate by code | Hiring/site access check | GET cert lookup | HIGH | DONE | GET /api/certificates/lookup/{code} | No QR flow documented
53 | Public Verifier | Download verified certificate PDF publicly | Attach to file | GET cert PDF by code | MEDIUM | DONE | GET /api/certificates/lookup/{code}/pdf
54 | Public Verifier | Browse public course catalog | Marketing site | GET courses | MEDIUM | DONE | GET /api/courses
30 | Subcontractor | Register own employees under subcontractor company | Site access requirement | POST users/invite | HIGH | DONE | POST /api/users/invite
31 | Subcontractor | Assign required NOM courses to own employees | Client requirement | POST enrollments/assign | HIGH | DONE | POST /api/enrollments/assign
32 | Subcontractor | Prove compliance to parent client | Audit | GET certificates admin all scoped; Share codes | HIGH | PARTIAL | GET /api/certificates/me; GET /api/certificates/lookup/{code} | Scoped list for subcontractor role unclear
33 | Subcontractor | Pay for course seats | Own budget | POST checkout | MEDIUM | PARTIAL | POST /api/payments/checkout | Provider webhook missing
34 | Subcontractor | View own team progress | Weekly review | GET enrollments; GET analytics learners | MEDIUM | PARTIAL | GET /api/enrollments; GET /api/analytics/learners | Analytics scoping to subcontractor not documented
35 | Subcontractor | Raise support ticket | Issue | POST support | LOW | DONE | POST /api/support/tickets
55 | Vendedor | Login as sales rep | Sales workflow | Would use POST auth/login | HIGH | DONE | POST /api/auth/login
56 | Vendedor | Register a new lead/prospect client | Sales call | Would need POST leads | HIGH | DONE
57 | Vendedor | Convert lead to paying client | Contract signed | Would POST company + link vendedor | HIGH | DONE | POST /api/companies
58 | Vendedor | View own sales pipeline | Weekly review | Would GET sales/pipeline | HIGH | DONE
59 | Vendedor | Track commission on client payments | Payment paid | Would GET commissions | MEDIUM | DONE
60 | Vendedor | Quote a course package to a prospect | Sales conversation | Would POST quote | MEDIUM | DONE
61 | Vendedor | See analytics filtered by own clients | Performance review | Would GET analytics scoped | MEDIUM | DONE

## Endpoints
Module | Method | Path | Purpose | Auth Requirement | Request Body | Response Keys | Status | Notes
analytics | GET | /api/analytics/courses | Per-course completion metrics | role:PRINCIPAL_ADMIN¦CLIENT_ADMIN |  | items | DONE
analytics | GET | /api/analytics/courses.csv | CSV export of course stats | role:PRINCIPAL_ADMIN¦CLIENT_ADMIN |  | csv | DONE
analytics | GET | /api/analytics/learners | Per-learner progress metrics | role:PRINCIPAL_ADMIN¦CLIENT_ADMIN |  | items | DONE
analytics | GET | /api/analytics/learners.csv | CSV export of learner stats | role:PRINCIPAL_ADMIN¦CLIENT_ADMIN |  | csv | DONE
analytics | GET | /api/analytics/overview | Top KPIs (users, courses, certs) | role:PRINCIPAL_ADMIN¦CLIENT_ADMIN |  | users, courses, certificates | DONE
analytics | GET | /api/analytics/overview.csv | CSV export of overview KPIs | jwt |  |  | DONE | Content-Type text/csv
analytics | GET | /api/analytics/report.pdf | PDF compliance report | role:PRINCIPAL_ADMIN¦CLIENT_ADMIN |  | binary | DONE
audit | GET | /api/audit | List audit events with filters | role:PRINCIPAL_ADMIN |  | items | DONE | Query: entityType, entityId, actorId, limit
auth | POST | /api/auth/change-password | User changes own password | jwt | currentPassword, newPassword | ok | DONE
auth | POST | /api/auth/forgot-password | Trigger reset email with token | public | email | ok | DONE | Depends on Mail module
auth | POST | /api/auth/login | Exchange email/password for JWT | public | email, password | token, user | DONE
auth | POST | /api/auth/logout | Blocklist current jti, revoke refresh | jwt | refreshToken? |  | DONE
auth | GET | /api/auth/me | Return current authenticated user | jwt |  | id, email, role, companyId | DONE
auth | POST | /api/auth/refresh | Rotate refresh token, return new pair | public | refreshToken | accessToken, refreshToken, expiresIn | DONE | Access token 15m, refresh 30d
auth | POST | /api/auth/reset-password | Consume reset token to set new password | public | token, newPassword | ok | DONE
certificates | POST | /api/certificates/:folio/email | Send DC-3 PDF by email | owner_or_admin | to | ok, delivered, sentTo | DONE | Falls back gracefully when mail not configured
certificates | PATCH | /api/certificates/:id | Admin update folio or expiry | role:principal_admin | folio?, expiryDate? | id | DONE | Audit-logged
certificates | GET | /api/certificates/admin/all | Admin list of certificates | role:PRINCIPAL_ADMIN |  | items | DONE
certificates | POST | /api/certificates/admin/issue | Manually issue a certificate | role:PRINCIPAL_ADMIN | userId, courseId, dc3Folio | id, code | DONE
certificates | GET | /api/certificates/lookup/{code} | Public verify by code | public |  | holder, courseTitle, issuedAt, status | DONE
certificates | GET | /api/certificates/lookup/{code}/pdf | Public PDF download by code | public |  | binary | DONE
certificates | GET | /api/certificates/me | List my certificates | jwt |  | items | DONE
certificates | POST | /api/certificates/{id}/email | Email certificate to holder | role:PRINCIPAL_ADMIN¦CLIENT_ADMIN |  | ok | DONE
certificates | GET | /api/certificates/{id}/pdf | Authenticated PDF fetch | jwt |  | binary | DONE
certificates | POST | /api/certificates/{id}/revoke | Revoke a certificate | role:PRINCIPAL_ADMIN | reason | ok | DONE
cfdi | POST | /api/cfdi/invoices | Stamp a CFDI for an existing invoice | role:principal_admin or invoice owner | invoice_id | id, cfdi_uuid, cfdi_xml_url, cfdi_status | DONE | Stub provider returns fake UUID + xml url
cfdi | GET | /api/cfdi/invoices/:id | Return CFDI status for an invoice | role:principal_admin or invoice owner |  | cfdi_uuid, cfdi_status | DONE
cfdi | POST | /api/cfdi/invoices/:id/cancel | Cancel a stamped CFDI | role:principal_admin | reason | cfdi_status, cfdi_canceled_at | DONE
companies | POST | /api/companies | Create client or subcontractor company | role:PRINCIPAL_ADMIN¦CLIENT | legalName, rfc, type, parentCompanyId | id | DONE
companies | GET | /api/companies | List companies | jwt |  | items | DONE
companies | GET | /api/companies/{id} | Get company detail | jwt |  | id, legalName | DONE
companies | PATCH | /api/companies/{id} | Update company | role:PRINCIPAL_ADMIN¦CLIENT | legalName, contactEmail, address | id | DONE
companies | DELETE | /api/companies/{id} | Deactivate company | role:PRINCIPAL_ADMIN |  | ok | DONE
companies | GET | /api/companies/{id}/subcontractors | List subcontractors of a client | jwt |  | items | DONE
courses | GET | /api/courses | Public catalog (published only) | public |  | items | DONE
courses | POST | /api/courses | Create course | role:PRINCIPAL_ADMIN | slug, titleEs, nomReference, priceMxn | id | DONE
courses | GET | /api/courses/admin/all | Admin catalog incl. unpublished | role:PRINCIPAL_ADMIN |  | items | DONE
courses | GET | /api/courses/slug/{slug} | Public course detail by slug | public |  | id, titleEs | DONE
courses | GET | /api/courses/{id} | Get course by id | jwt |  | id | DONE
courses | PATCH | /api/courses/{id} | Update course fields | role:PRINCIPAL_ADMIN | titleEs, priceMxn, isPublished | id | DONE
courses | DELETE | /api/courses/{id} | Delete course | role:PRINCIPAL_ADMIN |  | ok | DONE
courses | GET | /api/courses/{id}/modules | List modules of course | jwt |  | items | DONE
courses | PUT | /api/courses/{id}/modules | Upsert full module list | role:PRINCIPAL_ADMIN | modules | items | DONE
enrollments | POST | /api/enrollments | Self-enroll in a course | jwt | courseId | id | DONE | Auto-creates recert row if user already had a completed enrollment. 409 if active enrollment exists.
enrollments | GET | /api/enrollments | List enrollments (scoped) | jwt |  | items | DONE
enrollments | POST | /api/enrollments/assign | Bulk assign course to users | role:CLIENT_ADMIN¦CLIENT¦PRINCIPAL_ADMIN | courseId, userIds | count | DONE
enrollments | POST | /api/enrollments/bulk | Bulk enroll many users in a course | role:principal_admin or client_admin | course_id, user_ids | enrolled, skipped, enrollmentIds | DONE | Idempotent
enrollments | GET | /api/enrollments/me | List my enrollments | jwt |  | items | DONE
enrollments | DELETE | /api/enrollments/{id} | Cancel enrollment | jwt |  | ok | DONE
enrollments | GET | /api/enrollments/{id}/completions | List completed modules | jwt |  | items | DONE
enrollments | POST | /api/enrollments/{id}/modules/{moduleId}/complete | Mark module complete | jwt |  | ok | DONE
enrollments | GET | /api/enrollments/{id}/modules/{moduleId}/watch | Get video watch state | jwt |  | seconds, completed | DONE
enrollments | PATCH | /api/enrollments/{id}/modules/{moduleId}/watch | Report video watch progress | jwt | seconds | ok | DONE
enrollments | PATCH | /api/enrollments/{id}/progress | Update overall progress percent | jwt | progressPct | id, progressPct | DONE
enrollments | POST | /api/enrollments/{id}/recertify | Kick off recertification cycle | jwt |  | id | PARTIAL | Business rules for NOM expiry windows not verified
health | GET | /api/health | Service health probe | public |  | status | DONE
library | GET | /api/library/documents | Public list with filters | public | category?, industry?, search? | id, title, fileType, isFree, price | DONE
library | POST | /api/library/documents | Create document | role:principal_admin | title, fileType, fileUrl | id | DONE
library | GET | /api/library/documents/:id | Public detail | public |  | * | DONE
library | PATCH | /api/library/documents/:id | Update document | role:principal_admin | * | id | DONE
library | DELETE | /api/library/documents/:id | Soft delete (unpublish) | role:principal_admin |  |  | DONE
library | POST | /api/library/documents/:id/download | Record download and return file url | optional-jwt |  | file_url | DONE | Paid items return 402 unless purchased
library | POST | /api/library/documents/:id/purchase | Buy a paid document | jwt |  | id, purchased_at | DONE | Stub payment, no real charge
library | GET | /api/library/purchases/me | List my purchases | jwt |  | document_id, purchased_at | DONE
library | GET | /api/library/stats | Admin stats | role:principal_admin |  | total_documents, total_downloads, total_purchases, revenue_total | DONE
notifications | GET | /api/notifications | List notifications (unread filter) | jwt |  | items | DONE
notifications | PATCH | /api/notifications/:id/read | Mark one notification read | jwt |  | id | DONE
notifications | POST | /api/notifications/read-all | Mark all read | jwt |  | ok | DONE
notifications | PATCH | /api/notifications/read-all | Mark all current-user notifications read | jwt |  | count | DONE
notifications | GET | /api/notifications/unread-count | Unread badge count | jwt |  | count | DONE
notifications | POST | /api/notifications/{id}/read | Mark notification read | jwt |  | ok | DONE
payments | POST | /api/payments/:id/simulate-webhook | Admin simulates a webhook event | role:principal_admin | status | ok | DONE | Testing helper
payments | POST | /api/payments/checkout | Create checkout / payment intent | jwt | items | url, providerRef | PARTIAL | Provider webhook not exposed in swagger
payments | GET | /api/payments/invoices/{id}/pdf | Invoice PDF download | jwt |  | binary | DONE
payments | GET | /api/payments/me | List my payments | jwt |  | items | DONE
payments | GET | /api/payments/me/invoices | List my invoices | jwt |  | items | DONE
payments | POST | /api/payments/webhook | Public webhook to flip payment status | hmac-sha256 signature | provider_ref, status, amount, currency | ok | DONE | Uses x-webhook-signature header + WEBHOOK_SECRET env
quizzes | PUT | /api/quizzes | Upsert quiz for a course | role:PRINCIPAL_ADMIN | courseId, titleEs, passingScore, questions | id | DONE
quizzes | GET | /api/quizzes/admin/by-course/{courseId} | Admin view of quiz with answers | role:PRINCIPAL_ADMIN |  | id, questions | DONE
quizzes | GET | /api/quizzes/by-course/{courseId} | Learner view of quiz (no answer keys) | jwt |  | id, questions | DONE
quizzes | POST | /api/quizzes/{id}/attempts | Submit quiz attempt | jwt | answers | score, passed | PARTIAL | Max attempts enforcement / retake cooldown to be validated
sales | GET | /api/sales/commissions | Commission ledger | role:vendedor¦principal_admin |  | id, amount, status, period_month | DONE
sales | PATCH | /api/sales/commissions/:id | Approve or mark paid | role:principal_admin | status, paid_at | id | DONE
sales | POST | /api/sales/commissions/preview | Live-preview commission for a rule | jwt | rule, amount, package | pct, amount | DONE | Supports flat, package_tier, volume_tier, custom
sales | GET | /api/sales/dashboard/summary | Vendedor KPIs | role:vendedor¦principal_admin |  | quota_mtd, sold_mtd, pipeline_value, active_leads, commission_pending, commission_paid_ytd | DONE
sales | GET | /api/sales/deals | List closed deals | role:vendedor¦principal_admin |  | id, buyer_name, amount, commission_amount | DONE
sales | POST | /api/sales/deals | Close a deal, auto-calc commission | role:vendedor¦principal_admin | buyer_name, package, amount | id, commission_amount | DONE | Applies commission_rule from vendor_profile
sales | GET | /api/sales/leads | List leads scoped by role | role:vendedor¦principal_admin |  | id, company_name, status, expected_amount | DONE
sales | POST | /api/sales/leads | Create lead | role:vendedor¦principal_admin | company_name, contact_name, expected_amount | id | DONE
sales | PATCH | /api/sales/leads/:id | Update lead status or notes | role:vendedor¦principal_admin | status, notes | id | DONE
sales | DELETE | /api/sales/leads/:id | Delete lead | role:vendedor¦principal_admin |  |  | DONE
sales | GET | /api/sales/vendor-profile/:userId | Admin view profile | role:principal_admin |  | user_id, commission_rule | DONE
sales | PATCH | /api/sales/vendor-profile/:userId | Admin update rule | role:principal_admin | commission_rule, quota_monthly | user_id | DONE
sales | GET | /api/sales/vendor-profile/me | Own profile | role:vendedor |  | user_id, commission_rule, quota_monthly | DONE
support | POST | /api/support/tickets | Create support ticket | jwt | subject, message, priority | id | DONE
support | GET | /api/support/tickets | List all tickets (admin) | role:PRINCIPAL_ADMIN |  | items | DONE
support | GET | /api/support/tickets/me | List my tickets | jwt |  | items | DONE
support | PATCH | /api/support/tickets/{id} | Update ticket status/response | role:PRINCIPAL_ADMIN | status, response | id | DONE
training | POST | /api/agenda/appointments | Public book an appointment | public | requester_kind, requester_email, purpose, scheduled_at, assigned_user_id | id, status | DONE | status=requested until confirmed
training | GET | /api/agenda/available | Public list of bookable vendedores or capacitadores with slots | public |  | id, name, role, specialties, slots | DONE | Query ?purpose=demo¦consulting¦training
training | GET | /api/training/appointments | List own appointments | role:vendedor¦capacitador¦principal_admin |  | id, scheduled_at, purpose, status | DONE
training | PATCH | /api/training/appointments/:id | Confirm, cancel, or complete | role:vendedor¦capacitador¦principal_admin | status | id | DONE
training | GET | /api/training/dashboard/summary | Capacitador KPIs | role:capacitador¦principal_admin |  | sessions_this_month, hours_delivered, upcoming_appointments, avg_attendees | DONE
training | GET | /api/training/sessions | List sessions | role:capacitador¦principal_admin |  | id, title, scheduled_at, attendee_count, status | DONE
training | POST | /api/training/sessions | Create session | role:capacitador¦principal_admin | title, scheduled_at, duration_hours | id | DONE
training | PATCH | /api/training/sessions/:id | Update status | role:capacitador¦principal_admin | status, delivered_at | id | DONE
training | GET | /api/training/trainer-profile/:userId | View profile | role:principal_admin¦self |  | user_id, stps_registration | DONE
training | PATCH | /api/training/trainer-profile/:userId | Update profile | role:principal_admin¦self | bio, specialties, hourly_rate | user_id | DONE
training | GET | /api/training/trainer-profile/me | Own profile | role:capacitador |  | user_id, stps_registration, specialties | DONE
uploads | POST | /api/uploads | Upload file (multipart) | jwt | file | id, url | DONE
uploads | GET | /api/uploads/{id} | Serve/stream uploaded file | jwt |  | binary | DONE
users | GET | /api/users | List users scoped by role | jwt |  | items | DONE
users | POST | /api/users/invite | Invite user by email with role | role:PRINCIPAL_ADMIN¦CLIENT_ADMIN | email, firstName, lastName, role, companyId | id, email | DONE
users | GET | /api/users/me | Get own profile | jwt |  | id, email | DONE
users | PATCH | /api/users/me | Update own profile | jwt | firstName, lastName, locale, curp | id | DONE
users | GET | /api/users/{id} | Get user by id | jwt |  | id, email | DONE
users | PATCH | /api/users/{id} | Admin update user | role:PRINCIPAL_ADMIN¦CLIENT_ADMIN | firstName, lastName, role, isActive | id | DONE
users | DELETE | /api/users/{id} | Deactivate user (soft delete) | role:PRINCIPAL_ADMIN¦CLIENT_ADMIN |  | ok | DONE

## Data Model
Entity | Table | Key Fields | Relationships | Read Access | Write Access | Notes
Role | roles | code, label_es, label_en | referenced by users.role_code | Principal Admin, Client, Client Admin, Subcontractor, Employee | Principal Admin (seed only)
Company | companies | id, legal_name, rfc, type, parent_company_id, contact_email | hasMany User; hasMany Enrollment (payer); hasMany Payment; selfRef parent_company_id | Principal Admin, Client, Client Admin, Subcontractor | Principal Admin; Client (own record)
User | users | id, email, password_hash, first_name, last_name, role_code | belongsTo Company; hasMany Enrollment; hasMany Certificate; hasMany QuizAttempt; hasMany Payment | Principal Admin, Client, Client Admin, Subcontractor, Employee | Principal Admin; Client Admin (own company); Client (own company)
Course | courses | id, slug, title_es, title_en, description_es, description_en | hasMany CourseModule; hasMany Quiz; hasMany Enrollment | Principal Admin, all learners | Principal Admin
CourseModule | course_modules | id, course_id, position, title_es, title_en, content_url | belongsTo Course; hasMany ModuleCompletion; hasMany VideoWatch | Principal Admin, Employee | Principal Admin
Quiz | quizzes | id, course_id, title_es, passing_score, max_attempts, questions | belongsTo Course; hasMany QuizAttempt | Principal Admin, Employee | Principal Admin
QuizAttempt | quiz_attempts | id, quiz_id, user_id, score, passed, answers | belongsTo Quiz; belongsTo User | Employee, Principal Admin | Employee (self); auto-graded
Enrollment | enrollments | id, user_id, course_id, company_id, status, progress_pct | belongsTo User; belongsTo Course; belongsTo Company (payer); hasOne Certificate; hasMany ModuleCompletion; hasMany VideoWatch | Employee, Client, Client Admin, Subcontractor, Principal Admin | Principal Admin; Client Admin; Client
ModuleCompletion | module_completions | id, enrollment_id, module_id, completed_at | belongsTo Enrollment; belongsTo CourseModule | Employee | Principal Admin
VideoWatch | video_watches | id, enrollment_id, module_id, seconds, completed | belongsTo Enrollment; belongsTo CourseModule | Employee | Principal Admin
Certificate | certificates | id, enrollment_id, user_id, course_id, code, issued_at | belongsTo Enrollment; belongsTo User; belongsTo Course | Employee, Principal Admin, Public Verifier | Principal Admin; system (auto-issue)
Payment | payments | id, company_id, user_id, amount_mxn, currency, status | belongsTo Company; belongsTo User; hasOne Invoice | Client, Client Admin, Principal Admin | Principal Admin; system (webhook - MISSING)
Invoice | invoices | id, payment_id, company_id, number, cfdi_uuid, cfdi_xml_url | belongsTo Payment; belongsTo Company | Client, Client Admin, Principal Admin | Principal Admin; system (CFDI stamp - MISSING)
AuditLog | audit_log | id, actor_id, actor_email, actor_role, action, entity_type | belongsTo User (actor) | Principal Admin | system (write-only)
PasswordReset | password_resets | id, user_id, token, expires_at, used_at | belongsTo User | all | Principal Admin
LibraryItem | library_items | id, title, category, tags, file_id, visibility | belongsTo Upload | all authenticated | Principal Admin
Notification | notifications | id, user_id, title, body, read_at, created_at | belongsTo User | all authenticated | system
SupportTicket | support_tickets | id, user_id, subject, message, status, priority | belongsTo User | all authenticated | All authenticated (own tickets)
Upload | uploads | id, user_id, filename, mime, size, path | belongsTo User | all authenticated | All authenticated (own scope)
VendorProfile | vendor_profiles | id, user_id, employee_id, hire_date, quota_monthly, commission_rule | belongsTo User | Vendedor, Principal Admin | Principal Admin
TrainerProfile | trainer_profiles | id, user_id, stps_registration, rfc, hourly_rate, specialties | belongsTo User | Capacitador, Principal Admin | Principal Admin
SalesLead | sales_leads | id, vendedor_id, company_name, contact_name, status, expected_amount | belongsTo User (vendedor) | Vendedor, Principal Admin | Principal Admin
SalesDeal | sales_deals | id, vendedor_id, buyer_name, package, amount, commission_amount | belongsTo User (vendedor); belongsTo SalesLead | Vendedor, Principal Admin | Principal Admin
Commission | commissions | id, vendedor_id, deal_id, amount, status, period_month | belongsTo SalesDeal; belongsTo User (vendedor) | Vendedor, Principal Admin | Principal Admin
Appointment | appointments | id, requester_kind, requester_email, assigned_user_id, purpose, scheduled_at | belongsTo User (assigned_to) | Public, Vendedor, Capacitador, Principal Admin, Client Admin | Principal Admin
TrainingSession | training_sessions | id, capacitador_id, client_company_id, course_id, title, scheduled_at | belongsTo User (capacitador); belongsTo Company; belongsTo Course | Capacitador, Principal Admin, Client Admin | Principal Admin
RefreshToken | refresh_tokens | id, user_id, token_hash, expires_at, revoked_at | belongsTo User | all authenticated | Principal Admin
TokenBlocklist | token_blocklist | id, jti, expires_at |  | system | Principal Admin
PaymentWebhookEvent | payment_webhook_events | id, provider_ref, payload_json, verified | belongsTo Payment | Principal Admin | Principal Admin
LibraryDocument | library_documents | id, title, category, file_type, is_free, price | hasMany LibraryPurchase; hasMany LibraryDownload | all | Principal Admin
LibraryPurchase | library_purchases | id, user_id, document_id, amount, purchased_at | belongsTo User; belongsTo LibraryDocument | all authenticated | Principal Admin
LibraryDownload | library_downloads | id, document_id, user_id, downloaded_at | belongsTo LibraryDocument | system | Principal Admin

## Gaps and Blockers
A. Critical gaps (must fix before launch)
Priority | Category | Description | Impact | Suggested Fix | Owner | Blocked By
CRITICAL | Roles/Schema | Vendedor role not implemented (absent from roles seed + Role enum; no lead/commission entities). | Cannot track sales pipeline or pay commissions; blocks sales team onboarding. | Add VENDEDOR to roles seed + Role enum, add leads & commissions tables, add /api/leads and /api/commissions endpoints with guards. | Backend team | Client sign-off on commission model
CRITICAL | Roles/Schema | Capacitador (instructor) role not implemented; no instructor assignment or cohort/session entities. | Cannot assign a live instructor to a course or track cohorts. | Add CAPACITADOR role, cohorts + sessions tables, instructor assignment on courses, /api/cohorts endpoints. | Backend team | Client confirms cohort model
CRITICAL | Payments/Tax | No CFDI/SAT invoicing endpoint (invoices table has cfdi_uuid/cfdi_xml_url but no stamp/fetch endpoints). | Cannot issue tax-valid invoices in Mexico; blocks B2B sales. | Integrate Facturama or SW Sapien; add POST /api/invoices/:id/stamp and GET /api/invoices/:id/cfdi endpoints. | Backend team | Client picks CFDI provider
CRITICAL | Payments | No payment provider webhook endpoint; checkout creates provider_ref but no callback to mark paid. | Payments stay in pending state forever; certificates never unlock. | Add POST /api/payments/webhook with signature verification for chosen gateway (Conekta recommended). | Backend team | Client picks payment gateway
CRITICAL | Security | No refresh token or session revocation flow. JWT is fire-and-forget with no rotation. | Compliance risk for a regulated LMS; can't log out compromised sessions. | Add refresh_tokens table, POST /api/auth/refresh, POST /api/auth/logout with token blacklist. | Backend team
HIGH | Quiz | Quiz max_attempts enforcement and retake cooldown not verified in submit endpoint. | Employee could brute-force pass; violates 3-attempt policy. | Add attempt counter check + cooldown timer in POST /api/quizzes/:id/submit. | Backend team
HIGH | Certificates | Recertification cycle for NOM-specific expiry windows (annual for NOM-030) not modeled. | Certificates may not expire correctly; regulatory non-compliance. | Add validity_months per course; nightly cron to flip expired certs to status=expired. | Backend team | Client confirms expiry per course
HIGH | Certificates | No DC-3 folio auto-generation vs manual entry rules documented. | Folios may collide or miss STPS format. | Confirm PC-XXXX-XXXX-XXXX pattern; add sequence generator with STPS registration prefix. | Backend team | Client STPS registration number
HIGH | Users | No bulk user import (CSV/XLSX) endpoint. Client Admin onboarding hundreds of employees has no path. | Manual onboarding won't scale past pilot. | Add POST /api/users/bulk-import with async job + error report download. | Backend team
HIGH | Analytics | No role-based analytics scoping for Client (per-company drilldown) documented. | Client dashboards may leak cross-tenant metrics. | Add company_id filter guard on all analytics queries; add per-company drilldown views. | Backend team
HIGH | Content | No SCORM/xAPI ingestion for third-party course content. | Cannot accept industry-standard course packages. | Add SCORM 1.2/2004 player + xAPI LRS endpoint if in scope. | Backend team | Client confirms need
HIGH | Catalog | No public course catalog filter by NOM reference or category. | Public/marketing pages can't showcase by NOM. | Add ?nom= and ?category= query params to GET /api/courses/public. | Backend team
HIGH | Certificates | No QR code verification flow documented. | Verifiers can't scan certs; blocks trust model. | Add QR embed in DC-3 PDF pointing to /verify/:folio; document in API. | Backend team
HIGH | Certificates | No STPS DC-3 template compliance test; no digital signature (SAT) on PDFs. | Certs may be rejected by STPS auditors. | Snapshot official DC-3 template; implement layout test; add SAT digital signature step. | Backend team | Client provides template + signature
B. External blockers (waiting on client)
Priority | Question | Client Answer | What we still need | Owner
HIGH | Preferred payment gateway | Open to our recommendation | DECISION: recommend Conekta (cards + OXXO + SPEI, MX-native). Need client sign-off + merchant credentials. | Ale (client)
HIGH | CFDI / SAT invoicing provider | Yes, invoicing required | DECISION: recommend Facturama or SW Sapien. Need pick + API keys + RFC of issuing entity. | Ale (client)
HIGH | DC-3 format details (STPS registration, instructor name/RFC/folio, course codes, signer) | Certifier agent will confirm | Registration number, instructor details, STPS clave per NOM course, authorized signer name + signature image. | Certifier agent
HIGH | Course content (slides for 5 NOM courses + quiz banks + validity period) | Client provides slides; awaiting delivery | ETA on slide decks, quiz question banks with correct answers, validity months per course. | Ale (client) + certifier
HIGH | Hosting preference (we host vs client hosts) | Pending | DECISION needed; impacts monthly cost, SLAs, MX data residency setup. | Ale (client)
HIGH | Pricing model + package prices + seats per tier | Pending | One-time vs subscription? Prices per package (basic 5 NOM, extras). Seats included per tier. | Ale (client)