## Overview
PROCHEECK — Build Status vs. Spec
Compared against: Certifications web page (2).pdf + Pre-Build Requirements Checklist.docx
Legend
DONE | Built and working end-to-end (backend + frontend + tested)
PARTIAL | Basic version built; missing sub-features from spec
TODO | Not built yet; nothing blocks us from doing it
CLARIFY | Need input from client before we can build correctly
BLOCKED | Depends on an external decision (payment gateway, STPS, hosting, etc.)
Summary counts

## Features by Role
Role | Feature (from spec) | Status | What we built | Notes / gap
PRINCIPAL ADMIN
Principal Admin | All access | DONE | JWT + role guard; can access everything
Principal Admin | Upload courses (add, create, edit, delete) | DONE | POST/PATCH/DELETE /api/courses + admin UI at /dashboard/principal-admin/courses | Includes soft delete + publish toggle
Principal Admin | Assign courses | PARTIAL | Learner self-enrolls; admin can enroll any user via API | No admin bulk-assign UI yet (e.g. "auto-assign the DC-3 pack to a client's employees")
Principal Admin | Certificates: add, create, edit, delete | PARTIAL | Certs auto-issued on quiz pass + public verify + PDF | No admin UI to manually create/edit/revoke; no assign-cert flow
Principal Admin | Books/Manuals/Documents (Library) — add, edit, delete, assign | TODO | Nothing built | Whole Library module missing
Principal Admin | Users — add, edit, delete, permissions | DONE | Invite/list/update/deactivate at /api/users; UI at /dashboard/principal-admin/users | Uses role instead of granular permissions
Principal Admin | Monitoring results / Statistics and reports | DONE | /api/analytics/{overview,courses,learners} + UI at /dashboard/principal-admin/analytics | CSV/PDF export of reports not yet built
Principal Admin | Profile → Account (name, email, phone, address, timezone…) | TODO | Only email + role stored | Need phone, username, language, address, city/state/zip, timezone fields
Principal Admin | Profile → Support (help center, phone/email/live chat) | TODO | Nothing built | Live chat tool choice pending
Principal Admin | Right menu: Help + notifications | TODO | Nothing built
CLIENT
Client | Login | DONE | Email + password, JWT session
Client | Forgot password | DONE | Reset flow with tokenised email link | SMTP creds needed for real email delivery
Client | Two-step login (email first, then password) | TODO | Single-step form | Spec says "Once user enters email, password field is displayed"
Client | System Implementation / Config of training per industry | CLARIFY | Nothing built | Need to understand what "configuration" means in workflow terms
Client | Training Menu (My courses, Available courses, filter, status, score) | PARTIAL | Public catalog + My Courses list | No filter UI; no per-course status/score summary; no "recertify" button
Client | Section for Reviewing and Monitoring Contractor + Employee Certifications | PARTIAL | Analytics per learner shows completions/certs count | No per-employee cert-status view; no drill-down from Team page
Client | Team page — add member/subcontractor + available seats + team scores | PARTIAL | Team page shows own company + subcontractors; can add subcontractor | No "available seats" concept (depends on package pricing); no team score column
Client | Certificates table (name, number, issue/expiry, email, download, view) | PARTIAL | Employee cert page has code, course, issued, PDF download | Missing: expiry date, "send by email" button, expanded view modal
Client | Library (search + filter + books/manuals/documents) | TODO | Nothing built
Client | Statistics section | DONE | AnalyticsView on /dashboard/client/analytics (scoped)
Client | Profile → Account fields | TODO | See Principal Admin row
Client | Support / Live chat | TODO | Not built
Client | Only sees own subcontractors + employees (isolation) | DONE | RBAC enforced in analytics, users, companies, enrollments
CLIENT ADMIN
Client Admin | All client access to manage their team | DONE | Same feature set as Client + can invite users
Client Admin | Everything Client has (see rows above) | PARTIAL | Inherits Client status
Client Admin | Subcontractors auto-linked to client | DONE | Client Admin can only create subs under their own company; the sub is auto-linked
SUBCONTRACTOR
Subcontractor | Login | DONE
Subcontractor | System setup / Review client requirements | CLARIFY | Nothing built | Same clarification as Client — what does "system setup" mean per user?
Subcontractor | Assignment of training per industry/client requirements | TODO | Nothing built
Subcontractor | Add company employees | PARTIAL | Backend allows invite; UI page not yet added for Subcontractor role | Currently only Principal Admin and Client Admin have the Users page
Subcontractor | Training menu (courses) | PARTIAL | Can browse public catalog and see My Courses | Missing: filter, per-course status/score, recertify button
Subcontractor | Section for reviewing/monitoring employee certs | TODO | No sub-team view built | Should show employees under this subcontractor + their certs
Subcontractor | Statistics and reports | TODO | Analytics page not linked from Subcontractor dashboard | Backend endpoint allows it; need role added to the guard + a page
Subcontractor | Library | TODO | Nothing built
Subcontractor | Profile / Support / Notifications | TODO | Nothing built
Subcontractor | Only sees own subcontractor team (isolation) | DONE | RBAC scopes users/enrollments to own company
EMPLOYEE
Employee | Login + Forgot password | DONE
Employee | Profile → Account fields | TODO | Only name + email stored
Employee | Training Menu — My courses, Available, filter, status, score | PARTIAL | My Courses list + Catalog | Missing: filter, per-course score column, "recertify" action
Employee | Course open → Download cert / Send by email / Recertify | PARTIAL | Download PDF works | "Send by email" and "Recertify" not built
Employee | Certificates table (name, number, issue, expiry, email, download, view) | PARTIAL | Table shows code, course, issued date, PDF download | Missing: expiry date, email send, view modal with full details
Employee | Library — search + filter + books/manuals/documents | TODO | Nothing built
Employee | Profile → Support | TODO | Not built
Employee | Cannot see other employees' info (isolation) | DONE | RBAC + /users returns only self

## Public pages & flows
Screen / Flow | Requirement from spec | Status | What we built | Notes / gap
MAIN PAGE
Main page | Sections: Online courses, Consulting, Software, Login, Certifications search, Chat | PARTIAL | Home + Courses + Consulting + Software + Login + Certificate-lookup pages exist | No chat widget; content is placeholder — needs real copy + design
Login (public) | Email → then password field; forgot password; login button | PARTIAL | One-step email + password form; forgot-password link added | Not two-step yet
ONLINE COURSES
Courses catalog | Courses search + filter by price + Add to cart on each | PARTIAL | Grid of published courses + Add to cart works | No search bar, no price filter
CONSULTING
Consulting | Our services / On-site safety management / Training development pages | TODO | Placeholder page only | Copy + assets needed (spec references worksitesafety.ca pages as inspiration)
SOFTWARE
Software | Safety management platform + Online training subscription pages | TODO | Placeholder page only | Copy + assets needed (same worksitesafety.ca reference)
CART
Cart | Table (Product, Price, Qty, Subtotal) + coupon + totals + Proceed | PARTIAL | Full cart with per-line subtotal + IVA + total + checkout button | Missing: coupon/discount code input
CHECKOUT
Checkout / payment | Real payment gateway + CFDI invoice | PARTIAL | Stub "paid" flow + non-CFDI invoice PDF | BLOCKED on payment gateway choice (SPEI/OXXO/cards) + CFDI provider (Facturama, Bind ERP, etc.)

## Cross-cutting
Area | Requirement | Status | What we built | Notes
AUTH
Auth | JWT login for all 5 roles | DONE | Bcrypt + JWT, role in token
Auth | Forgot password + email link | DONE | Token hashed, 1-hour expiry, one-time use | SMTP creds required for real send; dev logs URL to console
Auth | First-login password change | DONE | Invited users forced through /change-password
Auth | Two-step login (email → then password) | TODO | Single-step now
Auth | Change password from account page | TODO | Available via /change-password but not linked from a profile UI
i18n
i18n | Spanish (default) + English toggle | DONE | next-intl, es.json/en.json, header toggle
i18n | Date format DD/MM/YYYY, timezone UTC-6 | PARTIAL | Locale used in PDF; UI dates use browser locale | Force MX locale on all date rendering
CERTIFICATES / DC-3
Certs | DC-3 format certificate | PARTIAL | PDF template exists; header, code, holder, course, NOM ref, revoked watermark | CLARIFY: exact DC-3 fields (instructor name/RFC/folio, STPS clave codes) — client will send from certifier
Certs | Public verify by code | DONE | Public /certificate-lookup + PDF download
Certs | Expiry / recertification cycle | TODO | expires_at field exists but never set | BLOCKED on validity period from certifier (12 months?)
Certs | Send certificate by email | TODO | Not built
PAYMENTS / INVOICING
Payments | Real payment gateway | TODO | Stub only | BLOCKED — waiting on gateway pick (Stripe MX / MercadoPago / Openpay / Conekta)
Payments | Accepted methods: cards, OXXO, SPEI | TODO | None wired | BLOCKED on gateway pick (all three supported by Conekta/Openpay/MercadoPago)
Payments | CFDI / SAT electronic invoice | TODO | Non-CFDI PDF invoice only | BLOCKED — need CFDI provider account (Facturama, SW Sapien, Bind ERP)
Payments | IVA 16% correctly applied | DONE | Line-item subtotal × 0.16 = IVA, added to total
Payments | Coupon / discount | TODO | Not built
Payments | Refund / cancellation policy | CLARIFY | Not built | CLARIFY: refund policy pending from client
COURSE CONTENT
Content | Video modules with progress tracking | DONE | Upload video, track position/duration, resume, auto-complete at ≥90%
Content | PDF / image / text / URL modules | DONE | All 4 types render in the player
Content | Full video must be watched before quiz? — spec: NO (can forward) | DONE | Quiz link always available; no gating
Content | Quiz — pass score, max attempts, gating | DONE | Quiz per course, configurable pass %, ≥90% recommended per spec, 3 attempts default
Content | Quiz score is stored per attempt | DONE | quiz_attempts row per submission
Content | The 5 basic NOM course videos+materials | CLARIFY | Only *Trabajo en alturas* seed course exists | Client provides slides; we produce narrated videos. All 5 pending
LIBRARY
Library | Books / manuals / documents section for every role | TODO | Nothing built | Depends on content from certifier + upload UI extension
REPORTS / EXPORT
Reports | Statistics and reports page | DONE | Analytics view (overview + per-course + per-learner)
Reports | PDF export | PARTIAL | Certificate + Invoice PDFs | No report/analytics PDF export
Reports | CSV / Excel export of analytics | TODO | Not built | Client wants both PDF and Excel
SUPPORT / CHAT
Chat | Live chat widget | TODO | Not built | CLARIFY: pick tool — Tawk.to / Intercom / WhatsApp
Support | Help center / support ticket | TODO | Not built
Support | WhatsApp / SMS notifications | CLARIFY | Not built | CLARIFY: needed or not?
HOSTING / OPS
Ops | Docker Compose deploy | DONE | postgres + backend + (frontend can run local)
Ops | Production hosting choice | CLARIFY | Local Docker only | CLARIFY: client hosts vs we host, and where (data-residency in MX)
Ops | Domain / DNS / SSL | TODO | Not set up | BLOCKED — awaiting domain choice
Ops | Backups / disaster recovery | TODO | DB volume only
LEGAL / COMPLIANCE
Legal | Privacy policy + Terms (LFPDPPP compliant) | TODO | Not built | Client to draft; we render
Legal | Cookie / consent banner | TODO | Not built
Legal | STPS registration as agente capacitador externo | BLOCKED | N/A on our side | BLOCKED — client + certifier pending
BRAND / DESIGN
Brand | Final logo, colors, fonts, favicon | CLARIFY | Placeholder brand | Logo attached in spec; colours to derive from logo; fonts pending
Brand | Final app / domain name | CLARIFY | Working name "PROCHEECK" | Full company name in legal process

## Client clarifications
# | Category | Question | Client answer so far | What we still need | Priority
1 | Brand | Final platform name and short name | Short name = PROCHEECK; company name in legal process | Final legal name once registered | Medium
2 | Brand | Domain name | Related to point 1 | Confirm domain and registrar access | Medium
3 | Brand | Logo | Attached | — | —
4 | Brand | Brand colors | Per logo | Exact hex codes for primary/secondary/accent | Low
5 | Brand | Fonts / typography | Not answered | Any preferred font family | Low
6 | Brand | Visual style reference | worksitesafety.ca (like but not exact) | — | —
7 | i18n | Languages | Spanish (default) + English | — | —
8 | i18n | Timezone / date format | UTC-6, DD/MM/YYYY | — | —
9 | Content | Who provides course content? | Client provides slides; we produce narrated videos | Delivery timeline for the 5 NOM slide decks | HIGH
10 | Content | Are the 5 NOM videos ready? | No — awaiting slides | ETA for slides so we can start production | HIGH
11 | Content | Who writes quiz questions? | Certifier agent will confirm | Actual question banks (with correct answers) for each course | HIGH
12 | Content | Passing score threshold | Certifier confirms; should be ≥90% | Confirm 90% (or higher) per course | Medium
13 | Content | Quiz attempts allowed | 3 | — | —
14 | Content | Must full video be watched before quiz unlocks? | No — video can be forwarded | — | —
15 | Content | Course/certificate validity period | Certifier confirms | Number in months (12 typical) | HIGH
16 | Content | Video hosting / delivery format | Not answered | MP4 on our storage? Or external CDN (Vimeo/Wistia)? | Medium
17 | DC-3 | STPS registration as agente capacitador externo | Certifier confirms | Registration number to print on certificates | HIGH
18 | DC-3 | Official DC-3 template / fields | Attached | Confirm which attachment; we implement exact layout | HIGH
19 | DC-3 | Instructor details (name, RFC, folio) | Certifier confirms | Values to print on each cert | HIGH
20 | DC-3 | STPS course codes / clave per course | Certifier confirms | Code per NOM course | HIGH
21 | DC-3 | Authorized issuer / signer | Certifier agent | Signature image + name/title | HIGH
22 | DC-3 | Certificate numbering scheme | Certifier confirms | Folio pattern (currently PC-XXXX-XXXX-XXXX) | Medium
23 | Payments | Preferred payment gateway | Open to our recommendation | DECISION — recommend Conekta (cards + OXXO + SPEI, MX-native) | HIGH
24 | Payments | Accepted payment methods | Cards + OXXO + SPEI | — | —
25 | Payments | CFDI / SAT invoicing required? | Yes | Pick CFDI provider — recommend Facturama or SW Sapien | HIGH
26 | Payments | Tax handling (IVA) | 16% IVA | — | —
27 | Payments | Merchant / legal entity that receives funds | In legal process | RFC + bank account of receiving entity | HIGH
28 | Payments | Pricing model + package prices | Pending | One-time / subscription? Prices per package (basic 5 NOM, extras) | HIGH
29 | Payments | Refund / cancellation policy | Pending | Policy text so we can implement rules | Medium
30 | Users | 5 roles confirmed? | Pending | Confirm no 6th role | Medium
31 | Users | Seats/license per client | Depends on package pricing | Once pricing is set: seats per tier | HIGH
32 | Users | How are clients created — self-signup or admin? | Not answered | DECISION needed | Medium
33 | Users | Existing user data to migrate? | Not answered | Yes/no + format if yes | Low
34 | Library | Who provides Library content? | Certifier agent; we personalize | Files + brand assets | Medium
35 | Library | File types + volume | Certifier confirms | PDF? DOCX? approx size + count | Medium
36 | Comms | Notification email address | Pending | e.g. no-reply@<domain> | Medium
37 | Comms | Live chat tool | Open to our recommendation | DECISION — recommend Tawk.to (free) or WhatsApp Business | Medium
38 | Comms | Support phone / email | Pending | — | Medium
39 | Comms | WhatsApp / SMS notifications | Not answered | Need Yes/No | Low
40 | Hosting | Hosting preference (we host vs client) | Pending | DECISION needed — impacts monthly cost + SLAs | HIGH
41 | Hosting | DNS / domain access | Related to point 1 | Once domain chosen, we need DNS access | Medium
42 | Hosting | Integrations (HR / ERP / SSO) | Not answered | Any current systems to integrate? | Low
43 | Hosting | Data residency (MX) | Yes — MX | Confirmed — pick MX region for cloud host | HIGH
44 | Legal | Privacy Policy + Terms (LFPDPPP) | To be drafted by client | Delivered text so we can add to footer | Medium
45 | Legal | Full legal company details for footer/invoices | Pending | Legal name + RFC + address | HIGH
46 | Legal | Cookie / consent banner | To be drafted | Text + which categories to disclose | Low
47 | Reports | Which metrics matter most | Pending | List of KPIs beyond what we already show | Medium
48 | Reports | Export formats | PDF + Excel | We currently have PDF; need CSV/XLSX export | Medium
49 | Project | Single point of contact | Ale | — | —
50 | Project | Launch deadline | End of 2026 | — | —
51 | Project | Review cadence | Weekly check-ins | — | —

## API endpoints built
Module | Method | Path | Auth | Purpose
Health | GET | /api/health | public | Service + DB health
Auth | POST | /api/auth/login | public | Login → JWT
Auth | GET | /api/auth/me | JWT | Current user
Auth | POST | /api/auth/change-password | JWT | Change password (also clears must_change flag)
Auth | POST | /api/auth/forgot-password | public | Send reset email
Auth | POST | /api/auth/reset-password | public | Consume token, set new password
Users | POST | /api/users/invite | PA/CA/C | Invite user (returns temp password)
Users | GET | /api/users | JWT | List users (scoped by role)
Users | GET | /api/users/:id | JWT | Get user (scoped)
Users | PATCH | /api/users/:id | JWT | Update user
Users | DELETE | /api/users/:id | JWT | Deactivate user
Companies | POST | /api/companies | PA/CA/C | Create client or subcontractor
Companies | GET | /api/companies | JWT | List (scoped)
Companies | GET | /api/companies/:id | JWT | Get
Companies | GET | /api/companies/:id/subcontractors | JWT | List subs of a client
Companies | PATCH | /api/companies/:id | JWT | Update
Companies | DELETE | /api/companies/:id | PA | Soft delete
Courses | GET | /api/courses | public | Public catalog (published)
Courses | GET | /api/courses/slug/:slug | public | Course by slug
Courses | GET | /api/courses/:id | public | Course by id
Courses | GET | /api/courses/admin/all | PA | All courses incl. drafts
Courses | POST | /api/courses | PA | Create
Courses | PATCH | /api/courses/:id | PA | Update
Courses | DELETE | /api/courses/:id | PA | Soft delete
Modules | GET | /api/courses/:id/modules | public | Course modules
Modules | PUT | /api/courses/:id/modules | PA | Replace module list
Enroll. | POST | /api/enrollments | JWT | Self or admin-assign
Enroll. | GET | /api/enrollments/me | JWT | My enrollments
Enroll. | GET | /api/enrollments | JWT | List (scoped)
Enroll. | PATCH | /api/enrollments/:id/progress | JWT | Manual progress
Enroll. | DELETE | /api/enrollments/:id | JWT | Cancel
Enroll. | GET | /api/enrollments/:id/completions | JWT | Modules completed
Enroll. | POST | /api/enrollments/:id/modules/:mid/complete | JWT | Mark module done
Enroll. | GET | /api/enrollments/:id/modules/:mid/watch | JWT | Video position (resume)
Enroll. | PATCH | /api/enrollments/:id/modules/:mid/watch | JWT | Report video position
Quizzes | PUT | /api/quizzes | PA | Upsert quiz for a course
Quizzes | GET | /api/quizzes/admin/by-course/:cid | PA | Admin quiz view
Quizzes | GET | /api/quizzes/by-course/:cid | JWT | Learner quiz view (no answers)
Quizzes | POST | /api/quizzes/:id/attempts | JWT | Submit attempt
Certs | GET | /api/certificates/lookup/:code | public | Verify by code
Certs | GET | /api/certificates/lookup/:code/pdf | public | Public cert PDF
Certs | GET | /api/certificates/me | JWT | My certs
Certs | GET | /api/certificates/:id/pdf | JWT | Owner-scoped cert PDF
Payments | POST | /api/payments/checkout | JWT | Stub-paid checkout + auto-enroll
Payments | GET | /api/payments/me | JWT | My payments
Payments | GET | /api/payments/me/invoices | JWT | My invoices
Payments | GET | /api/payments/invoices/:id/pdf | JWT | Owner-scoped invoice PDF
Uploads | POST | /api/uploads | PA | Upload PDF/image/video (25MB)
Uploads | GET | /api/uploads/:id | public | Serve file
Analytics | GET | /api/analytics/overview | PA/CA/C | Top-line metrics
Analytics | GET | /api/analytics/courses | PA/CA/C | Per-course stats
Analytics | GET | /api/analytics/learners | PA/CA/C | Per-learner activity

## Update 2026-07-13
PROCHEECK — Build status update (2026-07-13)
Area | Item | Status | Notes
Ops | Frontend containerized | DONE | docker-compose builds & runs Next.js standalone image on port 3000
Ops | Automated DB backups | DONE | pg_dump daily 03:00 UTC, 14-day retention (configurable), separate volume
Ops | GitHub Actions CI | DONE | Backend build, frontend build, docker compose build on push/PR
Ops | Production env template + deploy guide | DONE | .env.production.example + DEPLOY.md with Caddy reverse-proxy example
Ops | Sentry integration | DONE | Backend + frontend; opt-in via SENTRY_DSN / NEXT_PUBLIC_SENTRY_DSN
Backend | Swagger / OpenAPI docs | DONE | GET /api/docs; toggle with SWAGGER_ENABLED=false in prod
Backend | Certificate expiry reminders | DONE | Cron 08:00 daily; emails & in-app notifications at 30 / 15 / 1 day out
Backend | Admin audit log | DONE | audit_log table + GET /api/audit; logs cert issue/revoke, user invite/update/deactivate, company create/update/delete, course create/update/publish/unpublish/delete
Backend | DB seed extended | DONE | Now seeds 5 published NOM courses (009, 017, 002, 019, 036) alongside 5 demo users
Frontend | Support widget on dashboard | DONE | Users can open tickets from any dashboard page
Frontend | Modal replaces confirm() | DONE | Recertification & certificate revocation now use branded dialogs
Frontend | Consulting & Software pages | DONE | Marketing copy placeholders (may swap once client provides real copy)
Frontend | Audit log viewer | DONE | New /dashboard/principal-admin/audit page; search + expandable metadata
Blocked | Real NOM course content | BLOCKED | Need videos, materials, quiz banks from client
Blocked | Payment gateway | BLOCKED | Stripe / Mercado Pago / Conekta — client to pick
Blocked | CFDI e-invoice provider | BLOCKED | Currently plain PDF; needs SAT-stamped CFDI via Facturama/SW/Solcedi
Blocked | DC-3 exact format | BLOCKED | Need folio numbering scheme, agent seal, signatures from client
Blocked | Hosting choice | BLOCKED | AWS / DigitalOcean / Vercel+Railway — deploy guide is provider-agnostic
Blocked | Pricing model | BLOCKED | Per-seat / per-course / subscription — affects Team page "available seats"
Blocked | Legal texts | BLOCKED | Terms, Privacy, Aviso de Privacidad from client legal team
Blocked | Live chat tool | BLOCKED | Intercom / Crisp / Tawk — client to pick; slot is ready in the layout
Blocked | Brand assets | BLOCKED | Logo files, brand colors beyond primary blue
Blocked | Domain + SSL | BLOCKED | Waiting on domain choice; Caddy config in DEPLOY.md handles TLS automatically